## Risk Register
Risk Register
Sample document - fictional data - Northwind Retail, Customer Self-Service Portal (NWR-2026-014)
ID | Risk Description | Category | Probability (1-5) | Impact (1-5) | Risk Score | Response Strategy | Response Plan | Owner | Status
R-01 | Payment/returns vendor API integration delayed | Vendor | 3 | 4 | 12 | Mitigate | Start integration testing in sprint 2; weekly vendor check-ins | Jordan Lee | Open
R-02 | Lead developer may leave mid-project | Resource | 2 | 4 | 8 | Transfer | Cross-train a backup developer; document the codebase | Priya Shah | Open
R-03 | Stakeholders request out-of-scope features | Scope | 4 | 3 | 12 | Mitigate | Enforce change control; review backlog weekly | Priya Shah | Open
R-04 | Migrated order data contains errors | Data Quality | 3 | 3 | 9 | Mitigate | Validate sample records; run reconciliation report | Sam Patel | Open
R-05 | Customer PII exposed through the portal | Security | 2 | 5 | 10 | Avoid | Security review + MFA + encryption before launch | Nina Brooks | Open
R-06 | Cloud cost overrun during testing | Cost | 2 | 2 | 4 | Accept | Monitor usage; low priority | Priya Shah | Closed
Scale: Probability and Impact rated 1 (low) to 5 (high). Risk Score = Probability x Impact.