## Issue Log
Issue Log
Sample document - fictional data - Northwind Retail, Customer Self-Service Portal (NWR-2026-014)
ID | Issue Description | Date Raised | Severity | Priority | Owner | Status | Resolution / Workaround | Date Resolved
I-01 | Test server crashed during UAT setup | 2026-03-24 | High | High | Sam Patel | In Progress | Provisioning a temporary test server
I-02 | Login page rejects some valid users | 2026-03-18 | Critical | High | Aiko Kim | Resolved | Fixed case-sensitivity bug in the auth check | 2026-03-20
I-03 | Returns label PDF fails to generate on Safari | 2026-03-26 | Medium | Medium | Jordan Lee | Open | Workaround: use Chrome; fix scheduled sprint 9
I-04 | Order status lags ~30 min behind the system | 2026-03-10 | Medium | Low | Sam Patel | Resolved | Reduced data sync interval to 10 minutes | 2026-03-12