## Change Log
Change Log
Sample document - fictional data - Northwind Retail, Customer Self-Service Portal (NWR-2026-014)
CR ID | Change Requested | Requestor | Date Submitted | Type | Impact Summary | CCB Decision | Decision Date | Status
CR-001 | Add single sign-on (SSO) login | Maria Alvarez | 2026-02-10 | Scope | +5 days, +$4k; improves adoption | Approved | 2026-02-14 | In Development
CR-002 | Add live chat widget | Call Center Ops | 2026-02-20 | Scope | +3 weeks, +$22k; out of scope | Denied | 2026-02-24 | Closed
CR-003 | Move go-live from Jun 30 to Jul 14 | Priya Shah | 2026-03-05 | Schedule | +2 weeks to absorb UAT slip | Pending |  | Under Review
CR-004 | Add a temporary test server | Priya Shah | 2026-03-25 | Cost | +$1.2k; protects the UAT schedule | Approved | 2026-03-26 | Implemented