## RACI Matrix
RACI Matrix
Sample document - fictional data - Northwind Retail, Customer Self-Service Portal (NWR-2026-014)
Activity / Deliverable | Sponsor | PM | Business Analyst | Architect | Lead Dev | QA Lead | DevOps | IT Director
Approve business case & charter | A | R | C | I | I | I | I | C
Gather requirements | I | A | R | C | C | I | I | I
Design solution architecture | I | A | C | R | C | I | C | C
Develop portal features | I | A | C | C | R | I | I | I
Integrate vendor API | I | A | I | C | R | I | C | I
Security review | I | A | I | R | C | C | C | C
User acceptance testing | C | A | C | I | C | R | C | I
Deploy to production | I | A | I | C | C | C | R | C
Train call-center staff | C | A | R | I | I | I | I | I
Approve go-live | A | R | C | I | C | C | C | C
R = Responsible ¦ A = Accountable (one per row) ¦ C = Consulted ¦ I = Informed